## Sheet1
# | Function/Screen | Feature | Level* | Function/Screen Details | Iteration | Deadline | In Charge | Status
1 | Home Page | Public | Simple | It allow everyone can view and search product in website | Iteration 1 | 18/01 | Quang Tú | Complete
2 | Product Details | Public | Medium | Details like description, color, size, ... for customer to choose | Iteration 1 | 18/01 |  | Complete
3 | Product list | Public | Simple | Customer can see products that they have just searched | Iteration 1 | 18/01 |  | Complete
4 | User Login | Common | Simple | User will login with account | Iteration 1 | 18/01 | Đức Thái | Complete
5 | User Register | Common | Simple | Customer can register a new account here | Iteration 1 | 18/01 |  | Complete
6 | Reset Password | User | Simple | User can retrieve password when forgotten by confirming information via email | Iteration 1 | 18/01 | Linh Trang | In progress
7 | Change Password | User | Simple | It allow user can change new password | Iteration 1 | 18/01 |  | In progress
8 | Products List | Seller | Medium | seller views and manages all products | Iteration 1 | 18/01 | Xuân Thái | Not Start
9 | User Profile | User | Medium | User can view and update user's infomation | Iteration 1 | 18/01 |  | Not Start
10 | Blog Details | Seller | Simple | Content of a blog | Iteration 1 | 18/01 | Ngọc Thành | Not Start
11 | Blogs List | Public | Simple | List of all the blogs for visitor to read | literation 1 | 18/01 |  | Not Start