## Sheet1
# | Function/Screen | Feature | Level* | Function/Screen Details | Iteration | Deadline | In Charge | Status
1 | Home Page | Public | Simple | It allow everyone can view and search product in website | Iteration 1 | 18/01 | Quang Tú | Not Start
2 | Product Details | Public | Medium | Details like description, color, size, ... for customer to choose | Iteration 1 | 18/01 |  | Not Start
3 | Cart Details | Customer | Complex | List of all the products that have been added into the cart | Iteration 1 | 18/01 |  | Not Start
4 | User Login | Common | Simple | User will login with account | Iteration 1 | 18/01 | Đức Thái | Not Start
5 | User Register | Common | Simple | Customer can register a new account here | Iteration 1 | 18/01 |  | Not Start
7 | User Details | Admin | Medium | User can view information about account and update information | Iteration 1 | 18/01 |  | Not Start
8 | Reset Password | User | Simple | User can retrieve password when forgotten by confirming information via email | Iteration 1 | 18/01 | Linh Trang | Not Start
9 | Change Password | User | Simple | It allow user can change new password | Iteration 1 | 18/01 |  | Not Start
10 | User List | Admin | Medium | Admin manage accounts | Iteration 1 | 18/01 |  | Not Start
11 | Cart Completion (Place Order) | Customer | Medium | Customer can comfirm order information like shipping information,... or change it | Iteration 1 | 18/01 | Xuân Thái | Not Start
12 | User Profile | User | Medium | User can view and update user's infomation | Iteration 1 | 18/01 |  | Not Start
13 | My Orders (xem lịch sử order) (Tổng quát) | Customer | Medium | Customers can view history of orders | Iteration 1 | 18/01 |  | Not Start
14 | Order Details (chi tiết) | Customer | Medium | Seller views the detail of 1 of his orders | Iteration 1 | 18/01 | Ngọc Thành | Not Start
15 | Products List | Seller | Medium | seller views and manages all products | Iteration 1 | 18/01 |  | Not Start
16 | Feedback | Public | Medium | User can view feedback from other customer about a product | literation 2 | 18/01 |  | Not Start